## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | ezScores Testing
Program Manager | Zaim Mehić, Ensar Čevra, Adnan Humačkić
Project Manager | Zaim Mehić, Ensar Čevra, Adnan Humačkić
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 02.01.2025 | Zaim Mehić, Adnan Humačkić, Ensar Čevra | 1. Prerequisites : Logged in as manager 2. Go to www.ezscores.ba; 3. Click on "Kreiraj ekipu" button; 4. Fill in the "Naziv ekipe" field with 51 letter word; 5. Add 5 players to the team; 6. Click on "Kreiraj ekipu" button; 7. New team is created and home screen is opened; EXPECTED RESULT: The following error message is shown: "Naziv ekipe je predug" https://edufit-my.sharepoint.com/:i:/g/personal/zaim_mehic_edu_fit_ba/EWi7ol4akHhJoifUK4gCBikB58EeC5X_a-K8rBmDw5StYw?e=9IKEC3 | [6 empty] | New |  |  |  |  | New
2 | 02.01.2025 | Zaim Mehić, Adnan Humačkić, Ensar Čevra | 1. Prerequisites : Logged in as manager 2. Go to www.ezscores.ba; 3. Click on "Kreiraj ekipu" button; 4. Fill in the "Naziv ekipe" field with correct number of letters (1 <= num. of letters <= 50); 5. Click on "Choose file" button to insert an image file; 6. In the popup window change file type from "Image files" to "All files"; 7. Choose non-image type of file; 8. Add 5 players to the team; 9. Click on "Kreiraj ekipu" button; 10. New team is created and home screen is opened; EXPECTED RESULT: The following error message is shown: "Odabrani dokument mora biti tip dokumenta slika" https://edufit-my.sharepoint.com/:i:/g/personal/zaim_mehic_edu_fit_ba/EbjHhf3LV1dEkYKk8igf-XQB9MR8ZxRmAO8v8lgj7lzsFQ?e=b79ORW | [6 empty] | New |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 02.01.2025 | Zaim Mehić, Adnan Humačkić, Ensar Čevra | 1. Prerequisites : Logged in as manager, Competition status is "Prijave otvorene", maximum number of teams is not reached, time for applications is passed; 2. Go to www.ezscores.ba; 3. Click on "Takmičenja" link; 4. Click on the dummy competition; 5. Click on "Prijavi se" button apply; 6. Click on the team you want to apply with; 7. Click on "Pošalji prijavu" button; 8. Dialog popup with message "Uspješno ste prijavili ekipu na takmičenje"; EXPECTED RESULT: The following error message is shown: "Nažalost, vrijeme za prijave je završeno" https://edufit-my.sharepoint.com/:i:/g/personal/zaim_mehic_edu_fit_ba/ERAcEAVJJhZClQ3eDcYrBA8B9a1rbHuCbM9I2_NbcSZwaQ?e=OWudpM | [6 empty] | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 02.01.2025 | Zaim Mehić, Adnan Humačkić, Ensar Čevra | 1. Prerequisites : Logged in as manager, Competition status is "Prijave otvorene", maximum number of teams is not reached, time for applications is not passed; 2. Go to www.ezscores.ba; 3. Click on "Takmičenja" link; 4. Click on the dummy competition; 5. Click on "Prijavi se" button apply; 6. Click on the team you want to apply with; 7. Click on "Pošalji prijavu" button; 8. Dialog popup with message "Uspješno ste prijavili ekipu na takmičenje"; EXPECTED RESULT: The following error message is shown: "Nažalost, maksimalan broj ekipa na takmičenju je već dosegnut" https://edufit-my.sharepoint.com/:i:/g/personal/zaim_mehic_edu_fit_ba/ERAcEAVJJhZClQ3eDcYrBA8B9a1rbHuCbM9I2_NbcSZwaQ?e=OWudpM | [6 empty] | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 02.01.2025 | Zaim Mehić, Adnan Humačkić, Ensar Čevra | 1. Prerequisites : Logged in as manager, Competition status is "Prijave otvorene", maximum number of teams is reached, time for applications is passed; 2. Go to www.ezscores.ba; 3. Click on "Takmičenja" link; 4. Click on the dummy competition; 5. Click on "Prijavi se" button apply; 6. Click on the team you want to apply with; 7. Click on "Pošalji prijavu" button; 8. Dialog popup with message "Uspješno ste prijavili ekipu na takmičenje"; EXPECTED RESULT: The following error message is shown: "Nažalost, vrijeme za prijave je završeno i maksimalan broj ekipa je već dosegnut" https://edufit-my.sharepoint.com/:i:/g/personal/zaim_mehic_edu_fit_ba/ERAcEAVJJhZClQ3eDcYrBA8B9a1rbHuCbM9I2_NbcSZwaQ?e=OWudpM | [6 empty] | New | [6 empty] | Executing/Controlling | Design
6 | 05.01.2025 | Zaim Mehić, Adnan Humačkić, Ensar Čevra | 1. Prerequisites : Logged in as manager 2. Go to www.ezscores.ba; 3. Click on "Edit" button with pen icon for any team; 4. Click on "Naziv ekipe" field; 5. Remove all characters; 6. Loading indicator spins infinitely; EXPECTED RESULT: "Naziv ekipe" field is empty and ready for input. https://edufit-my.sharepoint.com/:i:/g/personal/zaim_mehic_edu_fit_ba/EfvEWAfZ0I9KheX2QHQUMRsBEMf-SskJ4FRobdcxTsNxIQ?e=e9tglv | [6 empty] | New | [6 empty] | Closing | Development
7 | 05.01.2025 | Zaim Mehić, Adnan Humačkić, Ensar Čevra | 1. Prerequisites : Logged in as organizator 2. Go to www.ezscores.ba; 3. Click on "+" button with to add create a competition; 4. Fill "Naziv" with valid name ("Turnir Mostar"); 5. Fill "Opis" with valid value ("Opis takmičenja"); 6. Fill "Maksimalan broj ekipa" with valid value (4); 7. Fill "Kotizacija" field with valid value (100) 7. Choose "Datum početka takmičenja" 8. Choose "Datum zavretka prijava" to be after "Datum početka takmičenja"; 9. Continue filling other values; EXPECTED RESULT: Error field appeares saying "Datum završetka prijava ne može biti veći od datum početka takmičenja" https://edufit-my.sharepoint.com/:i:/g/personal/zaim_mehic_edu_fit_ba/EYiBeHNVL4pJsoTqWeSs5S0BIua69zFHlmtVbz9tUivcKA?e=RKXbzV | [6 empty] | New | [7 empty] | Testing
8 | [17 empty] | Documentation and Training
9 | [17 empty] | Deployment
10 | [17 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).